## Summary
Apply the Service Standard in DfE
Version last updated: | 2022-12-01
View the full standards list sheet which you can filter by phase and standard.
These standards mirror the standards in the Apply the Service Standard in DfE service.
The following links will take you to the relevant standard in the DfE guidance
1. Understand users and their needs
2. Solve a whole problem for users
3. Provide a joined up experience across all channels
4. Make the service simple to use
5. Make sure everyone can use the service
6. Have a multidisciplinary team
7. Use agile ways of working
8. Iterate and improve frequently
9. Create a secure service which protects users’ privacy
10. Define what success looks like and publish performance data
11. Choose the right tools and technology
12. Make new source code open
13. Use and contribute to open standards, common components and patterns
14. Operate a reliable service

## Standards List
Point | Standard | Phase | Raw Guidance
1 | Understand users and their needs | Discovery | an understanding of the types and numbers of users who might use the service
1 | Understand users and their needs | Discovery | how the team articulate the problem to be solved
1 | Understand users and their needs | Discovery | how the team have involved and considered users with access needs
1 | Understand users and their needs | Discovery | how to demonstrate why the team selected the research methods they used
1 | Understand users and their needs | Discovery | well scoped research questions
1 | Understand users and their needs | Discovery | a variety of methods of user research
1 | Understand users and their needs | Discovery | a prioritised list of user needs
1 | Understand users and their needs | Discovery | an understanding of the difference between users and project stakeholders
1 | Understand users and their needs | Discovery | a Data Protection Impact Assessment (DPIA) (DfE Intranet Page) has been started, where necessary. If you do not have access to the DfE intranet, ask a civil servant to get the information for you
1 | Understand users and their needs | Discovery | a plan for alpha
1 | Understand users and their needs | Alpha | hypotheses related to user needs
1 | Understand users and their needs | Alpha | hypotheses tested with a variety of quick, throwaway prototypes
1 | Understand users and their needs | Alpha | collaboration with other service-related teams and stakeholders, including policy
1 | Understand users and their needs | Alpha | use of existing research and performance data across DfE
1 | Understand users and their needs | Alpha | clear definition of user needs written in language familiar to users
1 | Understand users and their needs | Alpha | clear definition of user groups
1 | Understand users and their needs | Alpha | a prioritised list of user stories
1 | Understand users and their needs | Alpha | how inclusive design is being considered in addition to testing with people with access needs
1 | Understand users and their needs | Alpha | an accessibility audit plan
1 | Understand users and their needs | Alpha | research that identifies parts of the service which users find difficult
1 | Understand users and their needs | Alpha | evidence of how the team iterated the service to make these parts easier for users and how this was tested and researched
1 | Understand users and their needs | Alpha | test and validate concepts with users with access needs
1 | Understand users and their needs | Alpha | show an understanding of the tools and technology users have access to
1 | Understand users and their needs | Alpha | a plan for private beta, including the eligibility criteria for real user participation and methods of measuring their experience
1 | Understand users and their needs | Alpha | research and thought into how the service will be maintained and supported
1 | Understand users and their needs | Alpha | how the service might need to scale in the future
1 | Understand users and their needs | Beta and Live | recommendations from most recent phase assessment have been addressed
1 | Understand users and their needs | Beta and Live | a plan for ongoing research and continuous improvement
1 | Understand users and their needs | Beta and Live | choosing the best methods to get results and feedback for the problems identified, not just relying on usability testing. Other methods you could use include a survey or analytics
1 | Understand users and their needs | Beta and Live | user research working with performance analysis to define success metrics
1 | Understand users and their needs | Beta and Live | how design and user needs have changed over time based on user research
1 | Understand users and their needs | Beta and Live | assisted digital routes, for example, offline or supporting routes, have been tested
1 | Understand users and their needs | Beta and Live | a third party accessibility audit of the service and actions taken based on findings
1 | Understand users and their needs | Beta and Live | a Data Protection Impact Assessment (DPIA) (intranet page) has been carried out, where neccessary. If you do not have access to the DfE intranet, ask a civil servant to get the information for you
1 | Understand users and their needs | Beta and Live | any neccessary security testing
1 | Understand users and their needs | Beta and Live | what the team has done beyond public beta to continue to meet user needs and deliver outcomes, when moving to live
2 | Solve a whole problem for users | Discovery | an understanding of the problem space (opens in new tab) and whether the proposed alpha addresses the full problem or leaves gaps
2 | Solve a whole problem for users | Discovery | whether there are services that exist that solve some - or the same - problem and how this service would fit in with existing services to solve a whole problem
2 | Solve a whole problem for users | Discovery | design and research to collaborate with policy and other teams who are delivering services (opens in new tab) for similar users
2 | Solve a whole problem for users | Discovery | an understanding of policy constraints and crossover with other services or DfE content
2 | Solve a whole problem for users | Alpha | evidence of where the service touches other services and whether you’ve spoken to those teams
2 | Solve a whole problem for users | Alpha | speaking to teams working on similar services to share knowledge of the types of users, user research carried out or design work done to meet user needs
2 | Solve a whole problem for users | Alpha | how the team will talk through an end-to-end journey at a service assessment
2 | Solve a whole problem for users | Alpha | an understanding of non-digital or off-line processes and their impact or relationship to the service
2 | Solve a whole problem for users | Alpha | how the service fits in with other channels or services relevant to your user group
2 | Solve a whole problem for users | Alpha | if you are providing a service to schools which will be used by people who use other DfE services, consider how to make the service consistent in the look and feel, the language used, and the tone of voice
2 | Solve a whole problem for users | Alpha | how the service will look and feel like other DfE services that are part of the same user journey
2 | Solve a whole problem for users | Alpha | creating a map of the current user journey, pain points and what the user journey will look like
2 | Solve a whole problem for users | Alpha | how to make it easy for users to focus on the next step in a journey. For example, how to navigate their way through the service to help them achieve their goal
2 | Solve a whole problem for users | Alpha | how the concepts being tested avoid duplication
2 | Solve a whole problem for users | Alpha | join together other relevant services or DfE content to solve a whole problem
2 | Solve a whole problem for users | Beta and Live | using research and private beta analytics to show the service works. Demonstrate, with evidence, how users can get through the end-to-end journey unaided, especially during public beta
2 | Solve a whole problem for users | Beta and Live | collaborating with teams that make part of the end-to-end service
2 | Solve a whole problem for users | Beta and Live | an understanding of - and research for - the full end-to-end journey, including online and offline journeys and GOV.UK content
2 | Solve a whole problem for users | Beta and Live | how support, including assisted digital channels, are working
2 | Solve a whole problem for users | Beta and Live | how users will know about the service, does it have a starting point on GOV.UK?
2 | Solve a whole problem for users | Beta and Live | offline processes and user support, including assisted digital (opens in new tab) routes, have been designed and tested, particularly at public beta
2 | Solve a whole problem for users | Beta and Live | an understanding of non-digital or off-line processes and their impact or relationship to the service
2 | Solve a whole problem for users | Beta and Live | user support process is in place
3 | Provide a joined up experience across all channels | Discovery | any channels that might be impacted by the policy intent or user needs. Speak with teams that work in any offline parts of the service, such as a call centre, and consider how an online service will affect them
3 | Provide a joined up experience across all channels | Discovery | what you might want to prototype and test at alpha
3 | Provide a joined up experience across all channels | Discovery | use of existing research and performance data across DfE
3 | Provide a joined up experience across all channels | Discovery | service and user journey mapping
3 | Provide a joined up experience across all channels | Alpha | data and research being used to improve offline and online channels
3 | Provide a joined up experience across all channels | Alpha | how you’ve explored where the service should start and stop
3 | Provide a joined up experience across all channels | Alpha | use of common components, such as DfE Sign-in, to provide a consistent experience with other DfE services
3 | Provide a joined up experience across all channels | Alpha | research with internal DfE teams who form part of the design of the service
3 | Provide a joined up experience across all channels | Alpha | entry points to the service. For example, how users find or know about it
3 | Provide a joined up experience across all channels | Alpha | how you might encourage users to use your digital service (opens in new tab)
3 | Provide a joined up experience across all channels | Alpha | gaps, drop off points, re-entry loops, transitions to other channels and returns to the service
3 | Provide a joined up experience across all channels | Alpha | how design, user research and content design are considering the full end-to-end service, including the non-digital parts, for example, branding of an email matches that of the service it is sent from
3 | Provide a joined up experience across all channels | Beta and Live | use of GOV.UK Design System (opens in new tab) and patterns or testing new patterns where needed
3 | Provide a joined up experience across all channels | Beta and Live | the right artefacts to describe the end-to-end service are being iterated and changed based on user research. For example service flows, blueprints, service maps
3 | Provide a joined up experience across all channels | Beta and Live | how users will find the service and entry points
3 | Provide a joined up experience across all channels | Beta and Live | a plan for how to onboard users to the service
3 | Provide a joined up experience across all channels | Beta and Live | the team observing and getting feedback on the end-to-end journey
3 | Provide a joined up experience across all channels | Beta and Live | performance data monitoring of drop out points
3 | Provide a joined up experience across all channels | Beta and Live | offline processes and user support, including assisted digital (opens in new tab) routes, have been designed and tested, especially during public beta
4 | Make the service simple to use | Discovery | evidence of how policy decisions can be implemented in a user-centred way
4 | Make the service simple to use | Discovery | use of plain English and language that users understand (opens in new tab)
4 | Make the service simple to use | Discovery | the types of users and scenarios relevant to the service
4 | Make the service simple to use | Discovery | using existing technologies, GOV.UK components and patterns (opens in new tab)
4 | Make the service simple to use | Discovery | developing your understanding of the user needs and pain points
4 | Make the service simple to use | Alpha | the user journey being simple to use (opens in new tab) and understand, and based on research
4 | Make the service simple to use | Alpha | risks associated with the service have been mitigated through design
4 | Make the service simple to use | Alpha | a consistent user experience with other DfE services
4 | Make the service simple to use | Alpha | the route users take to the service has been considered
4 | Make the service simple to use | Alpha | how the service will look and work on every browser or device users access it on (opens in new tab)
4 | Make the service simple to use | Alpha | offline elements, including assisted digital (opens in new tab) routes, have been considered
4 | Make the service simple to use | Alpha | a user-centred approach has been taken
4 | Make the service simple to use | Alpha | technology decisions supporting accessible and usable design
4 | Make the service simple to use | Alpha | content being tested to make sure that users understand it
4 | Make the service simple to use | Alpha | prototypes (opens in new tab) built and tested with users identified in discovery
4 | Make the service simple to use | Alpha | any unique component or pattern, or an adaptation of an existing component from the Design System (opens in new tab), are shared and tested. Plus, a plan for how you will keep them up-to-date with existing systems
4 | Make the service simple to use | Alpha | how users will report a problem with the service and how they’ll be supported and updated of any resolution
4 | Make the service simple to use | Beta and Live | how data has been used to understand service performance and a plan for how you’ll use this in live
4 | Make the service simple to use | Beta and Live | evidence of continuous improvement to make changes to the user journey or content
4 | Make the service simple to use | Beta and Live | continual monitoring of feedback and testing usability
4 | Make the service simple to use | Beta and Live | evidence of usability testing, including users with the lowest level of digital skills
4 | Make the service simple to use | Beta and Live | how the service meets accessibility requirements
4 | Make the service simple to use | Beta and Live | user research to understand any performance issues
5 | Make sure everyone can use the service | Discovery | time and money allocated for accessibility testing and audits at future phases
5 | Make sure everyone can use the service | Discovery | what your approach to recruiting users with access needs will be
5 | Make sure everyone can use the service | Discovery | evidence of talking to people who use assistive technology
5 | Make sure everyone can use the service | Discovery | user research with people with access needs
5 | Make sure everyone can use the service | Discovery | the context of your users environment
5 | Make sure everyone can use the service | Discovery | non-digital parts of the service, for example letters and phone calls
5 | Make sure everyone can use the service | Discovery | a content strategy based on user needs and policy intent
5 | Make sure everyone can use the service | Discovery | a plan for things you might test at alpha (opens in new tab)
5 | Make sure everyone can use the service | Alpha | testing the user journey with users
5 | Make sure everyone can use the service | Alpha | what your approach to recruiting users with access needs will be
5 | Make sure everyone can use the service | Alpha | exploring the support model, for example, what is the offline user journey? Is there a telephne number or email address for service support?
5 | Make sure everyone can use the service | Alpha | starting accessibility testing
5 | Make sure everyone can use the service | Alpha | inclusive design (opens in new tab) considering how age, gender and culture might impact the service
5 | Make sure everyone can use the service | Alpha | a plan for accessibility testing at beta
5 | Make sure everyone can use the service | Alpha | designing and testing content with users of the service
5 | Make sure everyone can use the service | Alpha | the context of your users environment when they might be using the service, for example, a noisy classroom, slow internet connection, and what devices they are using
5 | Make sure everyone can use the service | Alpha | how the service fits into wider DfE services
5 | Make sure everyone can use the service | Alpha | testing how assistive digital support will work
5 | Make sure everyone can use the service | Alpha | research with users across the digital inclusion scale
5 | Make sure everyone can use the service | Alpha | content written in plain English
5 | Make sure everyone can use the service | Beta and Live | continual testing with users with access needs
5 | Make sure everyone can use the service | Beta and Live | what your approach to recruiting users with access needs will be
5 | Make sure everyone can use the service | Beta and Live | the context of your users environment when they might be using the service, for example, a noisy classroom, slow internet connection, and what devices they are using
5 | Make sure everyone can use the service | Beta and Live | how you’ve tested - and continue to test - with users who need assistive digital support (opens in new tab)
5 | Make sure everyone can use the service | Beta and Live | an accessibility audit and any issues fixed, this is a mandatory requirement
5 | Make sure everyone can use the service | Beta and Live | how the service meets the latest accessibility standards
5 | Make sure everyone can use the service | Beta and Live | an accessibility statement that explains how accessible the service is. This needs to be published when the service moves into public beta
5 | Make sure everyone can use the service | Beta and Live | the service continues to be iterated based on insights from user research
5 | Make sure everyone can use the service | Beta and Live | any changes are tested to make sure they meet accessibility requirements
5 | Make sure everyone can use the service | Beta and Live | non-digital or off-line processes and their impact or relationship to the service
6 | Have a multidisciplinary team | Discovery | roles specific at discovery (opens in new tab) to the type of work that needs doing
6 | Have a multidisciplinary team | Discovery | if working with contractors (opens in new tab), create a plan for how knowledge will be shared
6 | Have a multidisciplinary team | Discovery | identify a service owner and consider how they will be engaged through the design and delivery of the service
6 | Have a multidisciplinary team | Discovery | identify where additional roles may be needed and how to fill them
6 | Have a multidisciplinary team | Alpha | the right team roles are in place to deliver the goal of the service at this stage
6 | Have a multidisciplinary team | Alpha | having people with the skills to understand data and what metrics you need to measure
6 | Have a multidisciplinary team | Alpha | a user researcher, responsible for research and usability tests
6 | Have a multidisciplinary team | Alpha | product and delivery managers with the knowledge and authority to make day-to-day decisions to improve the service
6 | Have a multidisciplinary team | Alpha | a plan to transfer knowledge and skills from contractors to permanent staff
6 | Have a multidisciplinary team | Beta and Live | how the team and ways of working can keep improving the service
6 | Have a multidisciplinary team | Beta and Live | how knowledge and skills from contractors have been transferred to permanent staff
6 | Have a multidisciplinary team | Beta and Live | how the team has evaluated and iterated the less common paths through the service
6 | Have a multidisciplinary team | Beta and Live | a plan for what team you’ll need to operate and support the service once live
6 | Have a multidisciplinary team | Beta and Live | knowledge and skills from contractors is transferred to permanent staff
7 | Use agile ways of working | All Phases | how the team use agile ways of working (opens in new tab), tools and techniques
7 | Use agile ways of working | All Phases | changes to the service are based on user research feedback and testing. The Family experience design history (opens in new tab) documents how they’ve done this
7 | Use agile ways of working | All Phases | how the team will prioritise riskiest assumptions
7 | Use agile ways of working | All Phases | evidence of decision making with senior stakeholders that allow the team to adapt and change
7 | Use agile ways of working | All Phases | evidence that governance is being managed with measurable goals
7 | Use agile ways of working | All Phases | the team has all the skills it needs at each phase of the agile lifecycle
8 | Iterate and improve frequently | All Phases | continued research and iteration based on feedback, data and metrics. Becoming a teacher design history (opens in new tab) documents how they’ve done this
8 | Iterate and improve frequently | All Phases | a process to review content and check that it’s up-to-date and reflects current policy, or is retired
8 | Iterate and improve frequently | All Phases | where team priorities lie and which improvements will deliver the most value
8 | Iterate and improve frequently | All Phases | methods to iterate and improve design when there are time constraints
8 | Iterate and improve frequently | All Phases | how the team will work together to prioritise a backlog
8 | Iterate and improve frequently | All Phases | how the team will deploy software regularly (opens in new tab)
8 | Iterate and improve frequently | All Phases | having the right people in the team to keep improving the service
9 | Create a secure service which protects users’ privacy | Discovery | building an awareness of DfE security policies (opens PDF on intranet page in new tab) and recognise which ones relate to the service
9 | Create a secure service which protects users’ privacy | Discovery | evidence that there has been engagement with Information Security and a response has been received to indicate how security assurance (opens intranet page in new tab) should proceed
9 | Create a secure service which protects users’ privacy | Discovery | evidence that a Data Protection Impact Assessment (DPIA) (opens intranet page in new tab) has been started, where necessary. If you do not have access to the DfE intranet, ask a colleague with access to get the information for you
9 | Create a secure service which protects users’ privacy | Discovery | evidence that a Departmental Security Assurance Model (DSAM) process (opens intranet page in new tab) has been started, where necessary. If you do not have access to the DfE intranet, ask a colleague with access to get the information for you
9 | Create a secure service which protects users’ privacy | Discovery | a plan that details headline General Data Protection Regulation (GDPR) requirements
9 | Create a secure service which protects users’ privacy | Discovery | identify the minimum personal information (opens in new tab) you need from users to provide the service
9 | Create a secure service which protects users’ privacy | Discovery | whether the service needs identity assurance or authentication. If it does, consider your approach to identifying and evaluating assurance and authentication methods that balances risks in a proportionate way. For example, using common components , such as DfE Sign-in
9 | Create a secure service which protects users’ privacy | Alpha | continue to work on the DPIA, where relevant
9 | Create a secure service which protects users’ privacy | Alpha | demonstrable evidence that the service you want to build is technically feasible and meets required security standards
9 | Create a secure service which protects users’ privacy | Alpha | if delivery and security are two competing risks, speak to your Senior Responsible Officer (SRO) to discuss impact and requirement
9 | Create a secure service which protects users’ privacy | Alpha | explore security anti-personas or bad actors for the service, if relevant
9 | Create a secure service which protects users’ privacy | Alpha | tech choices and common components you might use when you build your service
9 | Create a secure service which protects users’ privacy | Alpha | a plan for how the findings from checking technical feasibility and security compliance will be addressed in beta
9 | Create a secure service which protects users’ privacy | Alpha | how to protect users and the service from fraud (opens in new tab)
9 | Create a secure service which protects users’ privacy | Alpha | the use of cookies (opens in new tab) in the service
9 | Create a secure service which protects users’ privacy | Alpha | how you will manage and own risks through risk registers and Information Security Officers (ISOs)
9 | Create a secure service which protects users’ privacy | Beta and Live | evidence of addressing findings from alpha
9 | Create a secure service which protects users’ privacy | Beta and Live | findings of DPIA are being addressed
9 | Create a secure service which protects users’ privacy | Beta and Live | before going into private beta, do a penetration test if the service is a new service or a significant change is made to a new service. A significant change could be a change in scope, storing more data or opening up to customers
9 | Create a secure service which protects users’ privacy | Beta and Live | residual risks and mitigations security have been raised and assigned
9 | Create a secure service which protects users’ privacy | Beta and Live | demonstrable evidence of how services and data storage will be secured (opens in new tab) to prevent data loss, corruption and availability concerns, among others
9 | Create a secure service which protects users’ privacy | Beta and Live | how you’ve tested your service to ensure it doesn’t expose security risk, for example, testing against OWASP Top 10 (opens in new tab)
9 | Create a secure service which protects users’ privacy | Beta and Live | use of common components, such as DfE Sign-in if authentification is required, to secure your service
9 | Create a secure service which protects users’ privacy | Beta and Live | creating an asset register for the service
9 | Create a secure service which protects users’ privacy | Beta and Live | evidence that all risks to security have been addressed, when moving from beta to live
9 | Create a secure service which protects users’ privacy | Beta and Live | evidence that the security controls implemented are compliant with department standards
9 | Create a secure service which protects users’ privacy | Beta and Live | how you will eventually decommission the service. Consider if the service is needed for a specific time, or whether it's needed for longer
9 | Create a secure service which protects users’ privacy | Beta and Live | consider archive or retention policies and access requirements
9 | Create a secure service which protects users’ privacy | Beta and Live | how to support Freedom of Information (FOI) requests or Subject Access Requests (SARs)
9 | Create a secure service which protects users’ privacy | Beta and Live | security and vulnerability issues with any systems that aren't being actively monitored or maintained
10 | Define what success looks like and publish performance data | Alpha | define what you want to measure and why and how these measurements will be obtained. Potential options for collecting this data could include:
10 | Define what success looks like and publish performance data | Alpha | analytics which describe time spent on pages, heatmaps, if users start something but don’t finish it
10 | Define what success looks like and publish performance data | Alpha | performance data (opens in new tab) and reporting, to capture baseline measurements on service efficiency, timescales, service level agreements (SLAs)
10 | Define what success looks like and publish performance data | Alpha | qualitative data, which could include insights from users on the current as-is service captured via user research and feedback
10 | Define what success looks like and publish performance data | Alpha | evidence of finding baseline data, or why this is not available, with a plan to show how you will measure future success
10 | Define what success looks like and publish performance data | Alpha | evidence of how the team have iterated and improved metrics and data collection plans as you learn more about user needs
10 | Define what success looks like and publish performance data | Alpha | what metrics could you analyse to support or improve the service
10 | Define what success looks like and publish performance data | Beta and Live | measurement data agreed in the KPIs during alpha has been captured and collated
10 | Define what success looks like and publish performance data | Beta and Live | quantitative and qualitative data has been combined to measure where the benefits are being realised
10 | Define what success looks like and publish performance data | Beta and Live | demonstration of how the collated data provides evidence to show how the new service is performing for users
10 | Define what success looks like and publish performance data | Beta and Live | evidence of performance data being used to make decisions about how to fix problems and improve the service
10 | Define what success looks like and publish performance data | Beta and Live | engagement with business owners and stakeholders to help to make decisions using performance data
10 | Define what success looks like and publish performance data | Beta and Live | ways to collect metrics and data are iterated and improved as the team learns more about user needs
10 | Define what success looks like and publish performance data | Beta and Live | regularly publishing performance metrics (opens in new tab), these must include cost per transaction, user satisfaction, completion rate and digital take-up
10 | Define what success looks like and publish performance data | Beta and Live | when moving to live, learnings from metrics in beta are applied
11 | Choose the right tools and technology | All Phases | evidence that the team have considered different options to how the service will be delivered technically and the rationale for the chosen technical direction
11 | Choose the right tools and technology | All Phases | technology choices are technically feasible and security assured (opens in new tab)
11 | Choose the right tools and technology | All Phases | the tools the team will be using and why they are value for money
11 | Choose the right tools and technology | All Phases | how the tools and technology you choose meet accessibility standards, including Web Content Accessibility Guidelines (WCAG) 2.1 (opens in new tab)
11 | Choose the right tools and technology | All Phases | any constraints with legislation, contracts or technology that impact on the service
11 | Choose the right tools and technology | All Phases | align technology choices with the recommended tech stack (opens in new tab) used across DfE, where possible
11 | Choose the right tools and technology | All Phases | a working prototype, technical spikes, or proof of concept - using the chosen tools and technology - has been built and tested to prove that the architecture is fit for purpose
11 | Choose the right tools and technology | All Phases | architectural artefacts, decisions (opens in new tab) and plans have been documented, shared across your community and reviewed and assured (opens in new tab)
11 | Choose the right tools and technology | All Phases | evidence that the team will continue to re-evaluate and challenge previous decisions as new requirements are discovered
11 | Choose the right tools and technology | All Phases | demonstration that technology choices are sustainable (opens in new tab) longer term
12 | Make new source code open | All Phases | any code being produced should be open by default. If at any point the code was not publicly available, the team will be asked why, and without good reason, could fail an assessment.
13 | Use and contribute to open standards, common components and patterns | All Phases | teams have reached out to other teams and similar services to consider possible patterns, architecture components (opens in new tab) and tools
13 | Use and contribute to open standards, common components and patterns | All Phases | open source tools (opens in new tab) and frameworks have been chosen or considered as the basis for the service components
13 | Use and contribute to open standards, common components and patterns | All Phases | using GOV.UK Design System (opens in new tab) common components and patterns
13 | Use and contribute to open standards, common components and patterns | All Phases | evidence of a design history (opens in new tab) to keep track of design decisions, options explored and rationale for choices made
13 | Use and contribute to open standards, common components and patterns | All Phases | recording architecture decisions (opens in new tab) to track decisions and rationale
13 | Use and contribute to open standards, common components and patterns | All Phases | how to share and encourage use of new and existing patterns and architecture components within the wider DfE service community
14 | Operate a reliable service | All Phases | how the service maximises uptime (opens in new tab) and speed of response for the online part of the service
14 | Operate a reliable service | All Phases | that the service has the ability to deploy software changes regularly (opens in new tab), without significant downtime. For example, by minimising the effort involved in creating new environments and populating pre-production environments with test data
14 | Operate a reliable service | All Phases | consider creating continuous integration and continuous delivery pipelines (opens in new tab) from an early phase of the project
14 | Operate a reliable service | All Phases | having regular quality assurance (opens in new tab) and performance testing
14 | Operate a reliable service | All Phases | testing the service in an environment that protects users privacy that’s as similar to live as possible
14 | Operate a reliable service | All Phases | appropriate monitoring (opens in new tab) is in place, together with a proportionate, sustainable plan to respond to problems identified by monitoring - given the impact of problems on users and government
14 | Operate a reliable service | All Phases | agreeing recovery point objectives and recovery time objectives with the service owner
14 | Operate a reliable service | All Phases | capturing appropriate service-level agreements (SLAs), relevant to the service and documenting them in the architecture decision record (ADR)
14 | Operate a reliable service | All Phases | making sure that runbooks (opens in new tab) and operational processes are captured, for example, how incident requests will be handled
14 | Operate a reliable service | All Phases | the team’s approach to incident management, ensure it is defined and documented
14 | Operate a reliable service | All Phases | who will be responsible for supporting the service once live